## Sheet1
Sprint | Planned Story Points | Actual Story Points | Completed | Predicted Story Points Remaining | Actual Story Points Remaining | Delta
Prototype | 29.5 | 29.5 | 29.5 | 141 | 144 | -3
Webpage | 33 | 36 | 26 | 108 | 115 | -7
Batch | 33 | 43 | 28 | 75 | 87 | -12
Profiling | 37 | 56 | 0 | 38 | 87 | -49
Completion | 29.5 | 85.5 | 81 | 8.5 | 6 | 2.5
Docs and Demo | 8.5 | 8.5 | 8.5 | 0 | -2.5 | 2.5
Total: | 170.5 |  | 173

## Sheet2
Member | Expected Points | Actual Points
Cameron | 8.3333 | 10.5
Glen | 17.5 | 19
Nick | 13 | 19
Richard | 10.8333 | 1
James | 15.3333 | 21.5
Omar | 10 | 5
| 75 | 76

## Sheet3
Member | Hours per Member
Cameron | 6
Glen | 11
Nick | 12
Richard | 1
James | 8
Omar | 14
Member | Hours per Member
Cameron | 15
Glen | 28.5
Nick | 41.5
Richard | 8
James | 16
Omar | 14
Member | Hours per Member
Cameron | 30
Glen | 24.5
Nick | 47.5
Richard | 8
James | 37
Omar | 12

## Sheet4
Sprint | Nick | Cameron | Omar | Glen | James | Richard
Webpage | 12 | 6 | 14 | 11 | 8 | 1
Batch | 41.5 | 15 | 14 | 28.5 | 16 | 8
Completion | 47.5 | 30 | 12 | 24.5 | 37 | 8
Docs & Demo
Sprint | Nick | Cameron | Omar | Glen | James | Richard
Webpage | 5 | 7.5 | 4.5 | 4 | 4 | 1
Batch | 4 | 0.5 | 13 | 8 | 0.5 | 1.5
Completion | 19 | 10.5 | 5 | 19 | 21.5 | 1
Docs & Demo