## Sheet1
Sprint | Planned Story Points | Actual Story Points | Completed | Predicted Story Points Remaining | Actual Story Points Remaining | Delta
Prototype | 29.5 | 29.5 | 29.5 | 141 | 144 | -3
Webpage | 33 | 36 | 26 | 108 | 115 | -7
Batch | 33 | 43 | 28 | 75 | 87 | -12
Profiling | 37 | 56 | 0 | 38 | 87 | -49
Completion | 29.5 | 85.5 |  | 8.5 | 87 | -78.5
Docs and Demo | 8.5 | 8.5 |  | 0 | 87 | -87
Total: | 170.5 |  | 83.5

## Sheet2
Member | Expected Points | Actual Points
Cameron | 7.5 | 7.5
Glen | 7 | 4
Nick | 6 | 5
Richard | 4 | 1
James | 4 | 4
Omar | 4.5 | 4.5
| 33 | 26
Member | Expected Points | Actual Points
Cameron | 4 | 0.5
Glen | 9 | 8
Nick | 5 | 4
Richard | 4 | 1.5
James | 4 | 0.5
Omar | 4 | 13

## Sheet3
Member | Hours per Member
Cameron | 6
Glen | 11
Nick | 12
Richard | 1
James | 8
Omar | 14
Member | Hours per Member
Cameron | 15
Glen | 28.5
Nick | 41.5
Richard | 8
James | 16
Omar | 14