## Sheet1
Sprint | Planned Story Points | Actual Story Points | Completed | Predicted Story Points Remaining | Actual Story Points Remaining | Delta
Prototype | 29.5 | 29.5 | 29.5 | 141 | 144 | -3
Webpage | 33 | 36 | 26 | 108 | 115 | -7
Batch | 33 | 43 |  | 75 |  | 75
Profiling | 37 |  |  | 38 |  | 38
Completion | 29.5 |  |  | 8.5 |  | 8.5
Docs and Demo | 8.5 |  |  | 0 |  | 0
Total: | 170.5